## PROPOSED Shutdown November '24
Shutdown Proposed for the month of November 2024
SN | Name of Element | 2024-11-01 | [29 empty] | Time | Reason | Category
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
SHUTDOWNS PROPOSED BY PGCIL
1 | 132kV LOKTAK(NHPC)-IMPHAL | [30 empty] | CSD 31.10.24 17:00 Hrs to 23:59Hrs | For HTLS Reconducting Works-Construction related works under NERSS-XIX | Construction activities related shutdown.
2 | 132kV KHANDONG(NEEPCO)-KHLIEHRIAT-2 | [30 empty] | CSD 0700 Hrs to 23:59 Hrs | For Re-conductoring of the existing single AAAC Panther with ACCC HTLS Conductor under NERES-XX Project | Construction activities related shutdown. | bar: 2024-11-01 8 to 2024-11-01 30
3 | 132kV BADARPUR-KHLIEHRIAT-1 | [30 empty] | CSD 31.10.24 17:00 Hrs to 1800 Hrs | Continious shutdown forReconductoring of the existing single AAAC Panther with ACCC HTLS Conductor under NERES-XX Project | Construction activities related shutdown. | bar: 2024-11-01 1 to 2024-11-01 7
4 | 132kV SILCHAR-SRIKONA(ASSAM)-1 | [30 empty] | 0900 Hrs to 1700 Hrs | Replacement of static LBB relay with numerical Relay at AEGCL End along with testing and commissioning | Existing system improvement related shutdown. | bar: 2024-11-01 26
5 | 132kV SILCHAR-SRIKONA(ASSAM)-2 | [30 empty] | 0900 Hrs to 1700 Hrs | Replacement of static LBB relay with numerical Relay at AEGCL End along with testing and commissioning | Existing system improvement related shutdown. | bar: 2024-11-01 28
6 | 132kV JIRIBAM-HAFLONG LINE | [30 empty] | 0900 Hrs to 1700 Hrs | For Installation of TLA | Existing system improvement related shutdown. | bar: 2024-11-01 1 to 2024-11-01 23
7 | 132kV RC NAGR(NEEPCO)-AGARTLA(TRIPURA)-1 | [30 empty] | 1100 Hrs to 1500 Hrs | For Line Impedance Measurement. | Normal Maintenance related shutdown. | bar: 2024-11-01 13
8 | 132kV RC NAGR(NEEPCO)-AGARTLA(TRIPURA)-2 | [30 empty] | 0900 Hrs to 1700 Hrs | For Line Impedance Measurement and AR Testing. | Normal Maintenance related shutdown. | bar: 2024-11-01 13
9 | 132kV JIRIBAM-TIPAIMUKH(MANIPUR) | [30 empty] | 0800 Hrs to 1800 Hrs | For OPGW installation work under relaiable communication Scheme on long spans in the area of deep valleys/River crossing etc | Construction activities related shutdown.
10 | A/R of 132kV KHLIEHRIAT-KHLIEHRIAT(MePTCL)-1 | [30 empty] | 0800 Hrs to 1800 Hrs | NON - AUTO MODE required for OPGW installation works under Reliable Communication Scheme. | Construction activities related shutdown.
11 | A/R of 132kV KHANDONG(NEEPCO)-KHLIEHRIAT-2 | [30 empty] | 0800 Hrs to 1800 Hrs | NON - AUTO MODE required for OPGW installation works under Reliable Communication Scheme. | Construction activities related shutdown.
12 | A/R of 132kV BADARPUR-KHLIEHRIAT-1 | [30 empty] | 0800 Hrs to 1800 Hrs | NON - AUTO MODE required for OPGW installation works under Reliable Communication Scheme. | Construction activities related shutdown.
|  | 2024-11-01 1: 2024-11-01 |  |  | Category
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
220kV Transmission lines
13 | 220kV BONGAIGAON-SALAKATI-1 | [30 empty] | CSD0900 Hrs to 1700 Hrs | For replacement of existing old central break 220kV 89A, 89B, 89L and 89T Isolators by double break isolator. | Existing system improvement related shutdown. | bar: 2024-11-01 15 to 2024-11-01 29
14 | 220kV MISA-KOPILI(NEEPCO)-2 | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of Bay Equipments | Normal Maintenance related shutdown. | bar: 2024-11-01 11
15 | 220kV MARIANI-MOKOKCHUNG-1 | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of Bay Equipments | Normal Maintenance related shutdown. | bar: 2024-11-01 11
16 | 220kV MISA-KOPILI(NEEPCO)-3 | [30 empty] | 0900 Hrs to 1700 Hrs | For repairing of conductor between span 30-29 of 220 KV Misa Kopili TL CKT-III | Normal Maintenance related shutdown. | bar: 2024-11-01 1
17 | 220KV KATHALGURI(AEGCL)-MARIANI(PG) | [30 empty] | 0900 Hrs to 1700 Hrs | For replacement of conventional porcelain insulators by composite long rod polymer insulators at Power/Deep valley/River/SH/NH crossing locations | Existing system improvement related shutdown. | bar: 2024-11-01 12
18 | 220kV MARIANI(AEGCL)-KATHALGURI(AEGCL) | [30 empty] | 0900 Hrs to 1700 Hrs | For replacement of conventional porcelain insulators by composite long rod polymer insulators at Power/Deep valley/River/SH/NH crossing locations | Existing system improvement related shutdown. | bar: 2024-11-01 13
|  | 2024-11-01 1: 2024-11-01 |  |  | Category
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
400kV Transmission lines
19 | 400kV MISA-BALIPARA-1 | [30 empty] | 0900 Hrs to 1700 Hrs | For replacement of conventional porcelain insulators by composite long rod polymer insulators at Power/Deep valley/River/SH/NH crossing locations | Existing system improvement related shutdown. | bar: 2024-11-01 14
20 | 400kV MISA-BALIPARA-2 | [30 empty] | 0900 Hrs to 1700 Hrs | For replacement of conventional porcelain insulators by composite long rod polymer insulators at Power/Deep valley/River/SH/NH crossing locations | Existing system improvement related shutdown. | bar: 2024-11-01 15
21 | 400kV MISA-MARIANI-2 | [30 empty] | 0800 Hrs to 1800 Hrs | For replacement of conventional porcelain insulators by composite long rod polymer insulators at Power/Deep valley/River/SH/NH crossing locations | Existing system improvement related shutdown. | bar: 2024-11-01 18 to 2024-11-01 28
22 | 400kV MISA-MARIANI-1 | [30 empty] | 0800 Hrs to 1800 Hrs | For replacement of conventional porcelain insulators by composite long rod polymer insulators at Power/Deep valley/River/SH/NH crossing locations | Existing system improvement related shutdown. | bar: 2024-11-01 29 to 2024-11-01 30
23 | 400kV SILCHAR-P K BARI(STERLITE)-1 | [30 empty] | 0900 Hrs to 1700 Hrs | For SD nature defect rectification works at span loc. 102-103, 164-165, Loc.123 | Normal Maintenance related shutdown. | bar: 2024-11-01 20
24 | 400KV Balipara Bongaigaon CKT III | [30 empty] | 0900 Hrs to 1700 Hrs | For replacement of conventional porcelain insulators by composite long rod polymer insulators at Power/Deep valley/River/SH/NH crossing location | Existing system improvement related shutdown. | bar: 2024-11-01 26
25 | 400KV Balipara Bongaigaon CKT IV | [30 empty] | 0900 Hrs to 1700 Hrs | For replacement of conventional porcelain insulators by composite long rod polymer insulators at Power/Deep valley/River/SH/NH crossing location | Existing system improvement related shutdown. | bar: 2024-11-01 29
26 | 400KV Balipara Bongaigaon CKT II | [30 empty] | 1100 Hrs to 1600 Hrs | For testing and commissioning of replaced electromechanical LBB relay with Numerical relay (Micom P141) in bay no 411. | Existing system improvement related shutdown. | bar: 2024-11-01 13
27 | 400KV Balipara Bongaigaon CKT I | [30 empty] | 1100 Hrs to 1600 Hrs | For testing and commissioning of replaced electromechanical LBB relay with Numerical relay (Micom P141) in bay no 414. | Existing system improvement related shutdown. | bar: 2024-11-01 16
28 | 400kV ALIPURDUAR-Bongaigaon -1 | [30 empty] | 1100 Hrs to 1600 Hrs | For testing and commissioning of replaced electromechanical LBB relay with Numerical relay (Micom P141) in bay no 414. | Existing system improvement related shutdown. | bar: 2024-11-01 16
|  | 2024-11-01 1: 2024-11-01 |  |  | Category
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
220kV Salakati SS
29 | 132 kV side of ICT#1 Main Bay (Bay-No.-109) at Salakati SS | [30 empty] | 0900 Hrs to 1700 Hrs | Bay AMP Work of 109 Main Bay. 132 kV side of ICT#1 main bay will be charged through 132 KV Transfer bay. No outage of equipment. | Normal Maintenance related shutdown. | bar: 2024-11-01 12
30 | 220 KV Main bay of ICT#1 (Bay No.-201) at Salakati SS | [30 empty] | 0900 Hrs to 1700 Hrs | For dismantling of Existing Dropper connection from 89A isolator to 220kV Main Bus-I for replacement of Isolator. | Normal Maintenance related shutdown. | bar: 2024-11-01 13
31 | 50MVA,220/132kV ICT-1 AT SALAKATI | [30 empty] | 0900 Hrs to 1700 Hrs | Shutdown of ICT for testing of CTs in both HV and LV Side. AMP work of ICT#1. ICT#1 will be out of service. | Normal Maintenance related shutdown. | bar: 2024-11-01 14
32 | 220 kV Main Bus#1 at Salakati SS | [30 empty] | 0900 Hrs to 1700 Hrs | For dismantling and Reconnection of Existing Dropper connection from 89A isolator to 220kV Main Bus-I for replacement of Isolator in Bongaigain-1 line | Normal Maintenance related shutdown. | bar: 2024-11-01 15; 2024-11-01 28
33 | 220 kV Main Bus#2 at Salakati SS | [30 empty] | 09000 Hrs to 1700 Hrs | For dismantling and Reconnection of Existing Dropper connection from 89B isolator to 220kV Main Bus-I for replacement of Isolator in Bongaigain-1 line | Normal Maintenance related shutdown. | bar: 2024-11-01 16; 2024-11-01 29
400kV Bongaigaon SS
34 | TIE BAY NO 411 OF 400kV BUR-REACTOR-2 & BALIPARA-2 AT BONGAIGAON | [30 empty] | CSD 0900 Hrs to 1700 Hrs | For replacement of electromechanical LBB relay with Numerical relay (Micom P141) in bay no 411. | Existing system improvement related shutdown. | bar: 2024-11-01 12 to 2024-11-01 13
35 | 400kV,50MVAR BUS-REACTOR-2 | [30 empty] | 1100 Hrs to 1600 Hrs | For testing and commissioning of replaced electromechanical LBB relay with Numerical relay (Micom P141) in bay no 411. | Existing system improvement related shutdown. | bar: 2024-11-01 13
36 | TIE BAY NO.414 OF 400kV BALIPARA-1 & ALIPURDUAR-1 LINE AT BONGAIGAON | [30 empty] | CSD 0900 Hrs to 1700 Hrs | For replacement of existing electromechanical LBB relay (English electric) with numerical relay (Micom P141) in bay no 414. | Existing system improvement related shutdown. | bar: 2024-11-01 15 to 2024-11-01 16
400kV Balipara SS
37 | FSC of 400 KV Balipara-Bongaigaon-3 | [30 empty] | 09000 Hrs to 1700 Hrs | For Vegetation Cleaning | Normal Maintenance related shutdown. | bar: 2024-11-01 5
38 | FSC of 400 KV Balipara-Bongaigaon-4 | [30 empty] | 09000 Hrs to 1700 Hrs | For Vegetation Cleaning | Normal Maintenance related shutdown. | bar: 2024-11-01 6
39 | 400 KV, 50 MVAR BNC-1 LINE REACTOR | [30 empty] | 09000 Hrs to 1700 Hrs | AMP OF LINE REACTOR | Normal Maintenance related shutdown. | bar: 2024-11-01 8
40 | Tie bay of 400 KV Bus reactor-2 and ICT-2 (402bay) | [30 empty] | 09000 Hrs to 1700 Hrs | AMP works | Normal Maintenance related shutdown. | bar: 2024-11-01 12
41 | Main Bay of 315 MVA ICT-1 (404 bay) | [30 empty] | 09000 Hrs to 1700 Hrs | AMP works | Normal Maintenance related shutdown. | bar: 2024-11-01 18
42 | 220 KV Bus Coupler Bay | [30 empty] | 09000 Hrs to 1700 Hrs | AMP works | Normal Maintenance related shutdown. | bar: 2024-11-01 20
400kV BNC SS
43 | 400kV AC Filter 1 Sub Bank 1 (Z1.Z1) | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 9
44 | 400kV AC Filter 2 Sub bank 4 (Z2.Z4) | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 11
45 | 400kV AC Filter 2 Main Bay | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 8
46 | 800KV Pole 2 Main Bay | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 6
47 | 800KV Pole 2 Tie Bay | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 7
48 | 400KV AC Filter 1 Sub Bank 2 (Z1.Z2) | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 4
49 | 400KV AC Filter 1 Sub Bank 3 (Z1.Z3) | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 5
50 | 400KV AC Filter 2 Sub Bank 1 (Z2.Z1) | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 19
51 | 400KV AC Filter 2 Sub Bank 2 (Z2.Z2) | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 20
52 | 400KV AC Filter 2 Sub Bank 3 (Z2.Z3) | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 21
53 | 400KV Bus Reactor 1 Main Bay | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 12
54 | 400KV Bus Reactor 1 Tie Bay | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 13
55 | 400KV Bus Reactor 2 Tie Bay | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 15
56 | 400KV BNC Ranganadi 2 Main bay | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 18
57 | 400KV Bus Reactor 2 Main Bay | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 22
400kV Silchar SS
58 | 63MVAR,BUS REACTOR-1 AT SILCHAR | [30 empty] | 0900 Hrs to 1700 Hrs | AMP OF REACTOR | Normal Maintenance related shutdown. | bar: 2024-11-01 12
59 | 63MVAR BUS REACTOR Main Bay 404 at Silchar | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of the bay equipment | Normal Maintenance related shutdown. | bar: 2024-11-01 11
60 | 315MVA,400/200kV ICT-3 AT SILCHAR | [30 empty] | 0900 Hrs to 1700 Hrs | AMP OF ICT | Normal Maintenance related shutdown. | bar: 2024-11-01 14
61 | 200MVA,400/132kV ICT-1 AT SILCHAR | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of ICT and 132kV Side Bay 107 | Normal Maintenance related shutdown. | bar: 2024-11-01 16
62 | 400kV Main Bus 2 at Silchar | [30 empty] | 0900 Hrs to 1700 Hrs | AMP OF BUS | Normal Maintenance related shutdown. | bar: 2024-11-01 20
400kV Mariani SS
63 | 400kV Kohima-1 Main Bay at Mariani S/S (Bay -410) | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay Equipments by Mariani S/S. | Normal Maintenance related shutdown. | bar: 2024-11-01 15
64 | 400kV Kohima-1 & BR-2 Tie Bay at Mariani S/S (Bay-411) | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipments | Normal Maintenance related shutdown. | bar: 2024-11-01 16
65 | 400kV Kohima-2 Main Bay at Mariani S/S (Bay-413) | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipments | Normal Maintenance related shutdown. | bar: 2024-11-01 19
66 | 400kV Kohima-2 & Future Line Tie Bay at Mariani S/S (Bay-414) | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of bay equipments | Normal Maintenance related shutdown. | bar: 2024-11-01 20
400kV Misa SS
67 | 500MVA,400/220kV ICT-3 AT MISA | [30 empty] | 0800 Hrs to 1700 Hrs | GD(GAS DENSITY) TRIP LOGIC MODIFICATION WORKS | Existing system improvement related shutdown. | bar: 2024-11-01 5
68 | 315MVA,400/220kV ICT-2 AT MISA | [30 empty] | 0800 Hrs to 1700 Hrs | AMP of ICT and 220KV Side bay AMP | Normal Maintenance related shutdown. | bar: 2024-11-01 14
69 | 400kV Side ICT-2 Main BAY-(425) | [30 empty] | 0800 Hrs to 1700 Hrs | AMP of Bay Equipments | Normal Maintenance related shutdown. | bar: 2024-11-01 13
132KV Kumarghat SS
70 | 132kV 20MVAR Bus Reactor at Kumarghat SS | [30 empty] | 1000 Hrs to 1700 Hrs | AMP of Reactor | Normal Maintenance related shutdown. | bar: 2024-11-01 4
| Name of Element | 2024-11-01 1: 2024-11-01 | Time | Remarks | Category
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Interregional/International
71 | 220KV ALIPURDUAR-SALAKATI-1 | [30 empty] | 0900 Hrs to 1700 Hrs | Shutdown for bay AMP and testing of CT before warranty end executed under NERSS-XII. | Normal Maintenance related shutdown. | bar: 2024-11-01 10 to 2024-11-01 11
72 | 132kV SM.NAGAR(TSECL)-COMILLA(BANGLAD)-2 | [30 empty] | 0900 Hrs to 1700 Hrs | AMP of Bay equipments | Normal Maintenance related shutdown. | bar: 2024-11-01 15
73 | 132KV Bus II of SM Nagar SS(TSECL) | [30 empty] | 0100 Hrs to 14000Hrs | Rectification of Bus Isolator(89B) of Comilla II Bay for Facilating of charging the bay through Bus II in case of Bus I Shutdown. No outage of elements. All feeders connected to Bus II may be shifted to Bus I | Normal Maintenance related shutdown. | bar: 2024-11-01 15
SN | Name of Element | 2024-11-01 1: 2024-11-01 | Time | Reason | Category
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
SHUTDOWNS PROPOSED BY ASSAM
1 | 132KV DIMAPUR-BOKAJAN | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 6
2 | 132KV BOKAJAN-SARUPATHAR | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 12
3 | 132KV GOLAGHAT-MARIANI | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 5
4 | 132KV GOLAGHAT-SARUPATHAR | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 13
5 | 220KV SAMAGURI-MARIANI CKT 2 | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 13
6 | 220KV SAMAGURI-MARIANI CKT 2 | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 14
7 | 220KV SAMAGURI-SONABIL CKT 1 | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 18
8 | 220KV SAMAGURI-SONABIL CKT 2 | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 19
9 | 220KV SAMAGURI-JAWAHARNAGAR | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 5
10 | 220KV SAMAGURI-JAWAHARNAGAR | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 21
11 | 220KV SAMAGURI-JAWAHARNAGAR | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 4
12 | 220KV SAMAGURI-SONAPUR | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 13
13 | 220KV SAMAGURI-SONAPUR | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 20
14 | 220KV SONAPUR-SARUSAJAI | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 12
15 | 220KV SONAPUR-SARUSAJAI | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 25
16 | 220KV SARUSAJAI-JAWAHARNAGAR | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 16
17 | 220KV AMGURI-MARIANI | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 6
18 | 220KV AMGURI- NTPS | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 20
19 | 220KV AMGURI-NTPS | [30 empty] | 8:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 21
20 | 220kV TINSUKIA-KATHALGURI CKT 1 | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 5
21 | 220kV TINSUKIA-KATHALGURI CKT 2 | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 13
22 | 220KV TINSUKIA-NTPS | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 19
23 | 220KV TINSUKIA-NRPP | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 28
24 | 132KV GOHPUR-NALKATA CKT1 | [30 empty] | 7:00-14:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 5
25 | 132KV GOHPUR-NALKATA CKT1 | [30 empty] | 7:00-14:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 6
26 | 132KV GOHPUR-NALKATA CKT2 | [30 empty] | 7:00-14:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 12
27 | 132KV GOHPUR-NALKATA CKT2 | [30 empty] | 7:00-14:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 23
28 | 132 KV Pailapool- Jiribam line | [30 empty] | 9:00-16:00 | CORRIDOR CLEANING & MAINTENANCE OF LINE | Normal Maintenance related shutdown. | bar: 2024-11-01 6
29 | 132kV RUPAI-CHAPAKHOWA | [30 empty] | 8:30-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 2
30 | 132KV TINSUKIA-RUPAI | [30 empty] | 9:30-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 11
31 | 132KV RUPAI-MARGHERITA | [30 empty] | 9:30-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 16
32 | 220 KV AGIA-BTPS CKT 1 | [30 empty] | 9:00-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 4
33 | 220KV AGIA-BTPS CKT 1 | [30 empty] | 9:00-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 20
34 | 220KV AGIA-BTPS CKT 2 | [30 empty] | 9:00-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 6
35 | 220KV AGIA-BTPS CKT 2 | [30 empty] | 9:00-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 22
36 | 220KV AGIA-BOKO | [30 empty] | 9:00-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 11
37 | 220KV AGIA-BOKO | [30 empty] | 9:00-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 26
38 | 220KV MIRZA-AGIA | [30 empty] | 9:00-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 12
39 | 220KV MIRZA-AGIA | [30 empty] | 9:00-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 27
40 | 220KV MIRZA-BOKO | [30 empty] | 8:00-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 8
41 | 220KV MIRZA-BOKO | [30 empty] | 8:00-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 20
42 | 132 KV HAILAKANDI-DULLAVCHERRA | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 1
43 | 132 KV SRIKONA-PAILAPOOL | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 4
44 | 132 KV PANCHGRAM-HAILAKANDI | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 6
45 | 132 KV PANCHGRAM-LUMSHNONG | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 11
46 | 132 KV SRIKONA-PAILAPOOL | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 18
47 | 132 KV DULLAVCHERRA-DHARMANAGAR | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 27
48 | 132 KV DULLAVCHERRA-DHARMANAGAR | [30 empty] | 9:00-16:00 | PREVENTIVE MAINTENANCE & CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 28
49 | 220KV RANGIA-SALAKATI CKT 1 | [30 empty] | 8:00-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 26
50 | 220KV RANGIA-SALAKATI CKT 2 | [30 empty] | 8:00-16:00 | CORRIDOR CLEANING | Normal Maintenance related shutdown. | bar: 2024-11-01 28
51 | 315 MVA ICT-1 AT MIRZA | [30 empty] | 8:00-16:00 | ROUTINE TESTING AND MAINTENANCE WORK | Normal Maintenance related shutdown. | bar: 2024-11-01 21
52 | 400KV BUS 1 AT MIRZA | [30 empty] | 8:00-16:00 | MAINTENANCE WORK | Normal Maintenance related shutdown. | bar: 2024-11-01 19
53 | 400KV BUS 2 AT MIRZA | [30 empty] | 8:00-16:00 | MAINTENANCE WORK | Normal Maintenance related shutdown. | bar: 2024-11-01 26
54 | 220KV MIRZA-SSJI CKT 1 | [30 empty] | 8:00-16:00 | ROUTINE TESTING AND MAINTENANCE WORK | Normal Maintenance related shutdown. | bar: 2024-11-01 28
SN | Name of Element | 2024-11-01 1: 2024-11-01 | Time | Reason | Category
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
SHUTDOWNS PROPOSED BY MEGHALAYA
1 | 220 KV Killing-Misa Line-I | [30 empty] | 08:00hrs - 16:00hrs | For Lines maintenance work | Normal Maintenance related shutdown. | bar: 2024-11-01 5
2 | 220 KV Killing-Misa Line-II | [30 empty] | 08:00hrs - 16:00hrs | For Lines maintenance work | Normal Maintenance related shutdown. | bar: 2024-11-01 5
3 | 220 KV Killing-Misa Line-I | [30 empty] | 08:00hrs - 16:00hrs | Preventivemaintenance of Bus Isolator 89A | Normal Maintenance related shutdown. | bar: 2024-11-01 5
4 | 220kV/132kV 160MVA ICT# 1 at Killing Substation | [30 empty] | 08:00hrs - 16:00hrs | Preventivemaintenance of Bus Isolator 89A | Normal Maintenance related shutdown. | bar: 2024-11-01 5
5 | 220 kV Killing BUS A | [30 empty] | 08:00hrs - 16:00hrs | Preventive maintenance of Bus Isolator 89A, of MISA1, Bus coupler, ICT#1 | Normal Maintenance related shutdown. | bar: 2024-11-01 5
6 | 220 KV Killing-Misa Line-I | [30 empty] | 08:00hrs - 16:00hrs | For Lines maintenance work | Normal Maintenance related shutdown. | bar: 2024-11-01 6
7 | 220 KV Killing-Misa Line-II | [30 empty] | 08:00hrs - 16:00hrs | For Lines maintenance work | Normal Maintenance related shutdown. | bar: 2024-11-01 6
8 | 220 KV Killing-Mawngap Line-I | [30 empty] | 08:00hrs - 16:00hrs | For Lines maintenance work | Normal Maintenance related shutdown. | bar: 2024-11-01 11
9 | 220 KV Killing-Mawngap Line-II | [30 empty] | 08:00hrs - 16:00hrs | For Lines maintenance work | Normal Maintenance related shutdown. | bar: 2024-11-01 11
10 | 220 KV Killing-Mawngap Line-I | [30 empty] | 08:00hrs - 16:00hrs | For Lines maintenance work | Normal Maintenance related shutdown. | bar: 2024-11-01 12
11 | 220 KV Killing-Mawngap Line-II | [30 empty] | 08:00hrs - 16:00hrs | For Lines maintenance work | Normal Maintenance related shutdown. | bar: 2024-11-01 12
12 | 400/220/33 kV 315MVA ICT#4 at Killing Substation | [30 empty] | 08:00hrs - 16:00hrs | Preventive Maintenance of ICT # 4 | Normal Maintenance related shutdown. | bar: 2024-11-01 20
13 | 400/220/33 kV 315MVA ICT#4 at Killing Substation | [30 empty] | 08:00hrs - 16:00hrs | Preventive maintenance of 220kV Side Terminal Equipments | Normal Maintenance related shutdown. | bar: 2024-11-01 21
14 | 400/220/33 kV 315MVA ICT#3 at Killing Substation | [30 empty] | 08:00hrs - 16:00hrs | Testing Of ICT# 3 | Normal Maintenance related shutdown. | bar: 2024-11-01 26
15 | 400/220/33 kV 315MVA ICT#3 at Killing Substation | [30 empty] | 08:00hrs - 16:00hrs | Preventive maintenance of 220kV Side Terminal Equipments | Normal Maintenance related shutdown. | bar: 2024-11-01 27
16 | 400kV Killing Bus A and Bus B | [30 empty] | 08:00hrs of 11.11.2024 to16:00hrs of 15.11.2024(Continous) | Replacement of SF6 Gas and Molecular seives due to low dew point ( in CT B Chamber of 406 Bay .Gas from 406 89A, 89B, CT, CB has to be extracted so as to maintain diffirential pressure acoss the chambers. As the 89A and89B chamber which are live need to be dead before extraction of gas (only achieved by mean of Total 400kV bus Shutdown) | Normal Maintenance related shutdown. | bar: 2024-11-01 11 to 2024-11-01 15
SN | Name of Element | 2024-11-01 1: 2024-11-01 | Time | Reason | Category
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
SHUTDOWNS PROPOSED BY NTPC
1 | 400kv ICT#2 | [30 empty] | 0900 Hrs 04.11.2024 to 1800 Hrs 10.11.2024 (continuous basis) | If Shutdown in Oct 24 is deferred. Replacement of 400KV Bushings & For Bay equipment PM | Normal Maintenance related shutdown. | bar: 2024-11-01 3 to 2024-11-01 10
400KV BAY-9 of ICT#2 | bar: 2024-11-01 3 to 2024-11-01 10
220KV BAY-9 of ICT#2 | bar: 2024-11-01 3 to 2024-11-01 10
2 | 400KV LINE#1 | [30 empty] | 0900 Hrs 16.11.2024 to 1800 Hrs 16.11.2024 (continuous basis) | For Bay 2 equipments PM and alignment of 4-289B isolator of bay 2 & bus -2 as 4-289B is linked to BUS-2 | Normal Maintenance related shutdown. | bar: 2024-11-01 16 to 2024-11-01 17
400KV BAY-2 | bar: 2024-11-01 16 to 2024-11-01 17
400kv Bus -2 | bar: 2024-11-01 16 to 2024-11-01 17
400kv Bus COUPLER BAY -6 | bar: 2024-11-01 16 to 2024-11-01 17
3 | 400KV LINE#2 | [30 empty] | 0900 Hrs 16.11.2024 to 1800 Hrs 16.11.2024 (continuous basis) | For Bay 1 equipments PM and alignment of 4-189A isolator of bay 1 & bus -1 as 4-189A is linked to BUS-1 | Normal Maintenance related shutdown.
400KV BAY-1
400kv Bus -1
400kv Bus COUPLER BAY -6
SN | Name of Element | 2024-11-01 1: 2024-11-01 | Time | Reason | Category
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
SHUTDOWNS PROPOSED BY NEEPCO
AGBP, NEEPCO
1 | GTG 1 (33.5 MW) | [30 empty] | 00:00 hrs of 05/11/24 to 24:00 hrs of 07/11/24 | Retrofitting,testing and commissioning works of new 216 kV,10 kA station Medium Duty Gapless (Type-Polymer) Surge Arrester (LA) | Normal Maintenance related shutdown. | bar: 2024-11-01 5 to 2024-11-01 7
2 | GTG 3 (33.5 MW) | [30 empty] | 00:00 hrs of 08/11/24 to 24:00 hrs of 10/11/24 |  | Normal Maintenance related shutdown. | bar: 2024-11-01 8 to 2024-11-01 10
3 | STG 5 (33.5 MW) | [30 empty] | 00:00 hrs of 17/11/24 to 24:00 hrs of 19/11/24 |  | Normal Maintenance related shutdown. | bar: 2024-11-01 17 to 2024-11-01 19
4 | GTG 2 (33.5 MW) | [30 empty] | 00:00 hrs of 20/11/24 to 24:00 hrs of 22/11/24 |  | Normal Maintenance related shutdown. | bar: 2024-11-01 20 to 2024-11-01 22
5 | GTG 4 (33.5 MW) | [30 empty] | 00:00 hrs of 23/11/24 to 24:00 hrs of 25/11/24 |  | Normal Maintenance related shutdown. | bar: 2024-11-01 23 to 2024-11-01 25
6 | GTG 6 (33.5 MW) | [30 empty] | 00:00 hrs of 26/11/24 to 24:00 hrs of 28/11/24 |  | Normal Maintenance related shutdown. | bar: 2024-11-01 26 to 2024-11-01 28
7 | STG 1 (30 MW) | [30 empty] | 00:00 hrs of 29/11/24 to 24:00 hrs of 01/12/24 |  | Normal Maintenance related shutdown.
8 | STG 2 (30 MW) | [30 empty] | 00:00 hrs of 02/12/24 to 24:00 hrs of 04/12/24 |  | Normal Maintenance related shutdown.
9 | STG 3 (30 MW) | [30 empty] | 00:00 hrs of 05/12/24 to 24:00 hrs of 07/12/24 |  | Normal Maintenance related shutdown.
10 | Station Transformer 1 | [30 empty] | 00:00 hrs of 08/12/24 to 24:00 hrs of 10/12/24 |  | Normal Maintenance related shutdown.
11 | Station Transformer 2 | [30 empty] | 00:00 hrs of 11/12/24 to 24:00 hrs of 13/12/24 |  | Normal Maintenance related shutdown.
12 | 220 kV Bus Coupler | [30 empty] | 00:00 hrs of 14/12/24 to 24:00 hrs of 16/12/24 |  | Normal Maintenance related shutdown.
13 | L1 (Kath-New Mariani PG) | [30 empty] | 00:00 hrs of 11/11/24 to 24:00 hrs of 13/11/24 |  | Normal Maintenance related shutdown. | bar: 2024-11-01 11 to 2024-11-01 13
14 | L2 (Kath-Mariani),State | [30 empty] | 00:00 hrs of 14/11/24 to 24:00 hrs of 16/11/24 |  | Normal Maintenance related shutdown. | bar: 2024-11-01 14 to 2024-11-01 16